## Summary
Jumpspace OSS Launch Readiness
Metric | Value
Total items | 18
Done | 7
Done locally | 4
External | 7
P0 remaining external | 5
Launch posture | Local package/docs/workflow readiness is mostly complete. npm name check currently returns 404/unclaimed. External launch evidence remains gated on Netlify deploy, npm publish/install, and GitHub hosted settings.

## Launch Plan
ID | Task | Status | Priority | Evidence Type | Evidence | Current Result | Remaining Work
L-001 | Fix hanging CLI integration tests | Done | P0 | Local | src/cli.test.ts; vitest.config.ts | npm test passed 43 files / 171 tests.
L-002 | Package metadata and local release doctor | Done | P0 | Local | package.json; LICENSE; node dist/cli.js release doctor --json | Local blockers 0; local warnings 0; pack dry-run includes required files. | Re-check immediately before publish.
L-003 | OSS hygiene files | Done | P0 | Local | CHANGELOG.md; CONTRIBUTING.md; SECURITY.md; SUPPORT.md; CODE_OF_CONDUCT.md | Files added for public launch hygiene. | Review wording before announcement.
L-004 | GitHub PR and issue templates | Done | P0 | Local | .github/PULL_REQUEST_TEMPLATE.md; .github/ISSUE_TEMPLATE | Templates added for bugs, features, and security contact guidance. | Create labels in GitHub UI.
L-005 | GitHub workflows | Done locally | P0 | Local | .github/workflows/ci.yml; .github/workflows/jumpspace.yml | CI and Jumpspace PR assistant workflow files exist; unauthenticated GitHub API returned 404 for christopherrote/jumpspace. | Requires pushed GitHub Actions run.
L-006 | Dependabot | Done locally | P1 | Local | .github/dependabot.yml | Root npm, docs npm, and GitHub Actions update configs added. | Verify after repository push.
L-007 | Docs site URL configuration | Done locally | P0 | Local | docs/astro.config.mjs; docs/src/content/docs/deploy/netlify.md | Astro site uses DOCS_SITE_URL, Netlify URL, then local fallback. | Set DOCS_SITE_URL to final Netlify/custom domain.
L-008 | Docs build | Done locally | P0 | Local | npm --prefix docs test; npm --prefix docs run build | Docs structure and static build pass locally. | Verify hosted Netlify deployment.
L-009 | Jumpspace roadmap task | Done | P0 | Local | docs/specs/jumpspace-v0.md#JS-050 | JS-050 records launch readiness and external gaps.
L-010 | Jumpspace launch tracker | Done | P1 | Local | launch/jumpspace-launch-readiness.md; launch/jumpspace_oss_launch_plan.xlsx | Generic document-ticket tracker replaced by Jumpspace-specific status.
L-011 | npm registry check | Done | P0 | External | node dist/cli.js release doctor --check-registry --json; curl https://registry.npmjs.org/jumpspace | Direct registry HTTP check returned 404 on 2026-06-28, so the package name appeared unclaimed at check time. | Re-check immediately before publish.
L-012 | Public npm publish | External | P0 | External | npm publish --access public | Not run. | Needs npm credentials.
L-013 | Public install smoke test | External | P0 | External | npm install -g jumpspace; jumpspace release install-doctor --json | Not run. | Requires published package.
L-014 | Netlify deployment verification | External | P0 | External | Netlify production deploy URL | https://jumpspace.netlify.app returned 200, but /deploy/netlify/ returned 404; current docs deploy is not verified. | Deploy the current docs build and confirm the final URL.
L-015 | GitHub CI green | External | P0 | External | GitHub Actions CI run URL | Local workspace is not a git repo; unauthenticated GitHub API returned 404 for christopherrote/jumpspace. | Needs pushed repository branch.
L-016 | Branch protection | External | P1 | External | GitHub repository settings | Not verified locally. | Needs GitHub admin access.
L-017 | GitHub release notes and tag | External | P0 | External | CHANGELOG.md; gh release create v0.1.0 | Release notes draft source exists. | Needs tag and GitHub release.
L-018 | Private security advisories | External | P1 | External | GitHub security settings | SECURITY.md references private reporting. | Enable in GitHub UI.

## External Checks
ID | Check | Status | Command / Evidence | Blocker
E-001 | npm name/version available | Done | curl https://registry.npmjs.org/jumpspace returned HTTP 404 on 2026-06-28. | Re-check immediately before publish.
E-002 | npm package published | External | npm publish --access public | Requires npm credentials.
E-003 | Public install passes | External | npm install -g jumpspace | Requires public package.
E-004 | Netlify deploy is reachable | External | https://jumpspace.netlify.app returned 200, but /deploy/netlify/ returned 404. | Deploy the current docs build and confirm the final URL.
E-005 | GitHub CI green | External | GitHub API returned 404 for christopherrote/jumpspace without credentials. | Requires pushed GitHub repository.
E-006 | Branch protection enabled | External | GitHub repository settings | Requires admin access.
E-007 | GitHub release published | External | gh release create v0.1.0 | Requires tag and release permissions.

## Sources
Source | Purpose | Path
Jumpspace task | Launch readiness task | docs/specs/jumpspace-v0.md#JS-050
Local tracker | Human-readable launch status | launch/jumpspace-launch-readiness.md
Package doctor | Local release readiness | node dist/cli.js release doctor --json
Install doctor | Active binary freshness | node dist/cli.js release install-doctor --json
Docs build | Static docs verification | npm --prefix docs run build
CI workflow | Hosted validation plan | .github/workflows/ci.yml
PR assistant | Jumpspace PR comment workflow | .github/workflows/jumpspace.yml